## Deliverables, Ethics, DMP, Othe
Deliverables, Ethics, DMP, Other Reports for Project 776282
Deliverables, Ethics, DMP, Other Reports
WP No | Del Rel. No | Del No | Title | Description | Lead Beneficiary | Nature | Dissemination Level | Est. Del. Date (annex I) | Rev. Due Date | Receipt Date | Approval Date | Status
WP1 | D1.1 | D2 | Proto Gibbs sampler | Functional Commander2 implementation, with placeholders for new modules | UiO | Demonstrator | Public | 31 May 2018 |  | 31 May 2018 | 22 Jan 2020 | Approved
WP1 | D1.2 | D14 | Operational Gibbs sampler | Operational Commander2 with submodules available on GitHub | UiO | Other | Public | 28 Feb 2019 |  | 28 Feb 2019 | 22 Jan 2020 | Approved
WP1 | D1.3 | D20 | Final Gibbs/posterior products | Final sky maps and posterior ensembles | UiO | Other | Public | 31 Aug 2020 |  | 25 Nov 2020 |  | Submitted
WP2 | D2.1 | D3 | Prototype flagging module | Code uploaded to repository;basic interface to Commander | INAF | Demonstrator | Public | 31 May 2018 |  | 31 May 2018 | 22 Jan 2020 | Approved
WP2 | D2.2 | D6 | Final flagging module | Final validated code uploaded to GitHub | INAF | Other | Public | 31 Aug 2018 |  | 20 Sep 2018 | 22 Jan 2020 | Approved
WP3 | D3.1 | D11 | Protoype gain estimation module | Code uploaded to GitHub, and basic interface to Commander2 | INAF | Demonstrator | Public | 30 Nov 2018 |  | 01 Dec 2018 | 22 Jan 2020 | Approved
WP3 | D3.2 | D12 | Final gain estimation module | Final validated code uploaded to GitHub repository, and integrated into Commander2 | INAF | Other | Public | 28 Feb 2019 |  | 12 Mar 2019 | 22 Jan 2020 | Approved
WP4 | D4.1 | D7 | Prototype MADAM module | Code uploaded to GitHub; basic interface to Commander2 | UH | Demonstrator | Public | 31 Aug 2018 |  | 20 Sep 2018 | 22 Jan 2020 | Approved
WP4 | D4.2 | D13 | Tuned MADAM module | Final and validated code uploaded to GitHub, integrated into Commander2 | UH | Other | Public | 28 Feb 2019 |  | 28 Feb 2019 | 22 Jan 2020 | Approved
WP4 | D4.3 | D32 | Commander 4D map interface | Commander 4D map software interface for integrating BeyondPlanck data products with industry-standard external codes | UH | Other | Public | 30 Sep 2020 |  | 30 Nov 2020 |  | Submitted
WP5 | D5.1 | D18 | Beam-deconvolved map maker module | Code uploaded to GitHub, with fully operational interface to Commander2 | UH | Other | Public | 31 May 2019 |  | 21 Nov 2019 |  | Submitted
WP5 | D5.2 | D19 | Low-resolution noise covariance matrix module | Final and validiated code uploaded to GitHub | UH | Other | Public | 30 Nov 2019 |  | 03 Dec 2019 |  | Submitted
WP5 | D5.3 | D31 | Low-level visualization tools | Collection of Python visualization tools for low-level BeyondPlanck data | UH | Other | Public | 31 Oct 2020 |  | 30 Nov 2020 |  | Submitted
WP6 | D6.1 | D4 | Initial astrophysical sky model | Commander2 input parameter files, and links to both input and output data files. | UiO | Demonstrator | Public | 31 May 2018 |  | 31 May 2018 | 22 Jan 2020 | Approved
WP6 | D6.2 | D5 | Commander module | Component separation integrated into Commander2 | UiO | Other | Public | 31 May 2018 |  | 31 May 2018 | 22 Jan 2020 | Approved
WP6 | D6.3 | D15 | First astrophysical sky model products | Commander2 parameter files and resulting sky maps available for internal testing. | UiO | Demonstrator | Public | 28 Feb 2019 |  | 28 Feb 2019 | 22 Jan 2020 | Approved
WP6 | D6.4 | D21 | Final astrophysical sky model products | Final posterior mean and standard deviation maps and parameters available | UiO | Other | Public | 31 Aug 2020 |  | 30 Nov 2020 |  | Submitted
WP6 | D6.5 | D28 | Joint LFI-WMAP dipole estimate | Joint estimate of the CMB dipole from Planck-LFI and WMAP | UiO | Other | Public | 30 Nov 2020 |  | 30 Nov 2020 |  | Submitted
WP7 | D7.1 | D16 | Cosmological interpretation module | Power spectrum and parameter estimation codes uploaded to GitHub | UMIL | Other | Public | 28 Feb 2019 |  | 12 Mar 2019 | 22 Jan 2020 | Approved
WP7 | D7.2 | D22 | Scientific characterization | Final power spectrum and parameters; scientific papers drafted | UMIL | Other | Public | 31 Aug 2020 |  | 30 Nov 2020 |  | Submitted
WP7 | D7.3 | D27 | Paper release | Suite of papers submitted to international journals and the pre-print archive (arxiv.org) | UMIL | Report | Public | 30 Nov 2020 |  | 30 Nov 2020 |  | Submitted
WP8 | D8.1 | D23 | Systematic error assessment | Assessment available in the form of a report; summarized in scientific paper | UMIL | Other | Public | 31 Aug 2020 |  | 25 Nov 2020 |  | Submitted
WP8 | D8.2 | D24 | Systematic error simulations | Sky map simulations available | UMIL | Other | Public | 31 Aug 2020 |  | 01 Dec 2020 |  | Submitted
WP9 | D9.1 | D1 | GitHub repository | Functional GitHub repository with skeleton directory structure for both scientific codes, reproducibility framework, and papers. All internal collaboration members are provided read and write access; external users are only provided read access. | PLANETEK HELLAS | Other | Public | 31 Mar 2018 |  | 03 Apr 2018 | 22 Jan 2020 | Approved
WP9 | D9.2 | D9 | Project web page | Web page hosted by the University of Oslo, publicly available | PLANETEK HELLAS | Websites, patents filling, etc. | Public | 31 Aug 2018 |  | 03 Oct 2018 | 22 Jan 2020 | Approved
WP9 | D9.3 | D10 | WP methodology report | First report available on project web page | PLANETEK HELLAS | Report | Public | 31 Aug 2018 |  | 03 Oct 2018 | 22 Jan 2020 | Approved
WP9 | D9.4 | D17 | Reproducible research methodology report | Report available on home page | PLANETEK HELLAS | Report | Public | 28 Feb 2019 |  | 12 Mar 2019 | 22 Jan 2020 | Approved
WP9 | D9.5 | D25 | Reproducibilty framework tool | Final framework available for download on home page | PLANETEK HELLAS | Other | Public | 30 Nov 2020 |  | 01 Dec 2020 |  | Submitted
WP9 | D9.6 | D26 | Product delivery | Final products uploaded to Planck Legacy Archive | PLANETEK HELLAS | Other | Public | 30 Nov 2020 |  | 30 Nov 2020 |  | Submitted
WP10 | D10.1 | D8 | Data management plan | First version of plan available; will be a living document | UiO | ORDP: Open Research Data Pilot | Public | 31 Aug 2018 |  | 20 Sep 2018 | 22 Jan 2020 | Approved
WP10 | D10.2 | D29 | First Interim report - for the period months 1 to 12 | Interrim report for Months 1-12 | UiO | Report | Public | 31 Mar 2019 |  | 21 Nov 2019 |  | Submitted
WP10 | D10.3 | D30 | Second Interim report - for the period months 13 to 21 | Second Interim report - for the period months 13 to 21 | UiO | Report | Public | 30 Nov 2019 |  | 23 Dec 2019 |  | Submitted